Digital Student ID Wallet App
Trello Board Structure & Project Schedule

Part 1: Trello Board Setup
Board Name: Digital Student ID Wallet - The Thinkers
Board Columns (Lists)
Column Name	Purpose
Backlog	All tasks waiting to be done
To Do (This Week)	Tasks prioritized for current week
In Progress	Tasks currently being worked on
Review/Testing	Tasks completed but need checking
Done	Completed tasks
Blocked	Tasks stuck waiting for something

Part 2: Complete Task Cards by Column
COLUMN 1: BACKLOG (All Tasks)

🟦 Planning & Requirements Cards
Card Title	Description	Labels	Assigned To
Create Requirements Document	Write detailed requirements with all features	Documentation	Durgesh Bin
Review Requirements with Team	Team meeting to approve requirements	Meeting	All
Create Data Dictionary	Define all data fields and types	Data	Krishna Bhandari
Design Database Structure	Create ER diagram for student data	Data, Technical	Krishna Bhandari
Security Requirements Analysis	Research and document security needs	Security	Manikkuwadura De Silva

🟩 Design Cards
Card Title	Description	Labels	Assigned To
Wireframe Login Screen	Draw rough sketch of login screen	Design	Md Mehedi Hasan
Wireframe ID Card Screen	Draw rough sketch of main ID screen	Design	Md Mehedi Hasan
Wireframe Profile Screen	Draw rough sketch of profile screen	Design	Md Mehedi Hasan
Create High-Fidelity Mockups	Design final UI in Figma	Design	Md Mehedi Hasan
Design QR Code Layout	Decide where QR code appears	Design	Md Mehedi Hasan
Create App Icon	Design app icon with university colors	Design	Md Mehedi Hasan
Create Splash Screen	Design loading screen	Design	Md Mehedi Hasan

🟨 Development Setup Cards
Card Title	Description	Labels	Assigned To
Set Up GitHub Repository	Create repo, add collaborators	Dev, Setup	Sarfraj Ahmad
Create Project Structure	Set up folders and files	Dev, Setup	Sarfraj Ahmad
Set Up Firebase Project	Create Firebase account and project	Dev, Backend	Manikkuwadura De Silva
Configure Firebase Authentication	Set up email/password login	Dev, Backend	Manikkuwadura De Silva
Set Up Firebase Database	Create Firestore database	Dev, Backend	Manikkuwadura De Silva
Set Up Development Environment	Install Android Studio/Xcode	Dev, Setup	Sarfraj Ahmad, Md Mehedi Hasan

🟧 Backend Development Cards
Card Title	Description	Labels	Assigned To
Create Student Data Schema	Define database collections	Backend, Data	Krishna Bhandari
Create API Endpoints	Build endpoints for student data	Backend	Sarfraj Ahmad
Implement Data Encryption	Encrypt sensitive student data	Backend, Security	Manikkuwadura De Silva
Create Mock Student Data	Generate 10 test student records	Data, Testing	Krishna Bhandari
Upload Mock Data to Firebase	Populate database with test data	Backend	Krishna Bhandari
Set Up Security Rules	Configure Firebase security rules	Security	Manikkuwadura De Silva

🟪 Frontend Development Cards
Card Title	Description	Labels	Assigned To
Build Login Screen UI	Create login screen layout	Frontend	Md Mehedi Hasan
Connect Login to Firebase	Implement authentication logic	Frontend	Md Mehedi Hasan
Build ID Card Screen UI	Create main ID card layout	Frontend	Sarfraj Ahmad
Display Student Photo	Load and display profile photo	Frontend	Sarfraj Ahmad
Display Student Details	Show name, ID, course	Frontend	Sarfraj Ahmad
Implement QR Code Generator	Create QR from student ID	Frontend	Sarfraj Ahmad
Add QR Refresh Timer	Auto-refresh QR every 5 min	Frontend, Security	Sarfraj Ahmad
Build Profile Screen UI	Create profile screen	Frontend	Md Mehedi Hasan
Implement Logout Function	Add logout functionality	Frontend	Md Mehedi Hasan
Add Offline Storage	Cache ID data locally	Frontend	Sarfraj Ahmad
Implement "Remember Me"	Stay logged in feature	Frontend	Md Mehedi Hasan

🟥 Testing Cards
Card Title	Description	Labels	Assigned To
Create Test Plan	Document testing approach	Testing	Krishna Bhandari
Test Login Functionality	Test all login scenarios	Testing	Krishna Bhandari
Test ID Card Display	Verify all fields show correctly	Testing	Durgesh Bin
Test QR Code Generation	Test QR generation and scanning	Testing	Durgesh Bin
Test Offline Mode	Test app without internet	Testing	Krishna Bhandari
Security Testing	Try to hack/breach the app	Security, Testing	Manikkuwadura De Silva
User Acceptance Testing	Test with real students	Testing	Durgesh Bin
Bug Fixing	Fix issues found in testing	Dev, Testing	Sarfraj Ahmad, Md Mehedi Hasan

🟫 Deployment Cards
Card Title	Description	Labels	Assigned To
Generate Signed APK	Create release build for Android	Deployment	Sarfraj Ahmad
Create App Store Listing	Write description, upload screenshots	Deployment	Sarfraj Ahmad
Submit to Google Play	Upload APK to Play Store	Deployment	Sarfraj Ahmad
Prepare User Guide	Create PDF instructions	Documentation	Md Mehedi Hasan
Prepare Launch Announcement	Write email to students	Communication	Durgesh Bin
Launch Day Monitoring	Watch for issues on launch day	Monitoring	All

🟪 Project Management Cards
Card Title	Description	Labels	Assigned To
Create Project Timeline	Set deadlines for all tasks	Management	D Abeysinghe Mudiyanselage
Schedule Weekly Meetings	Set up recurring team meetings	Management	D Abeysinghe Mudiyanselage
Create Contact List	Share everyone's contacts	Management	D Abeysinghe Mudiyanselage
Daily Standup (Ongoing)	15-minute daily check-in	Management	D Abeysinghe Mudiyanselage
Update Trello (Ongoing)	Keep board updated	Management	D Abeysinghe Mudiyanselage
Risk Register	Track potential issues	Management	D Abeysinghe Mudiyanselage

Part 3: Week-by-Week Schedule
WEEK 1 (Feb 16 - Feb 22) - Planning & Setup

Monday, Feb 16
Time	Activity	Lead	Participants
10:00 AM	Kickoff Meeting	D Abeysinghe	All
11:00 AM	Create Trello Board	D Abeysinghe	-
2:00 PM	Start Requirements Document	Durgesh	-

Tuesday, Feb 17
Task	Assigned To	Due
Complete Requirements Draft	Durgesh	End of day
Start Data Dictionary	Krishna	End of day
Research Security Requirements	Manikkuwadura	End of day
Create GitHub Repo	Sarfraj	End of day

Wednesday, Feb 18
Task	Assigned To	Due
Review Requirements Draft	All (in meeting)	11:00 AM
Finalize Requirements	Durgesh	5:00 PM
Start Wireframes	Mehedi	End of day

Thursday, Feb 19
Task	Assigned To	Due
Complete Data Dictionary	Krishna	3:00 PM
Complete Security Analysis	Manikkuwadura	3:00 PM
Continue Wireframes	Mehedi	End of day

Friday, Feb 20
Task	Assigned To	Due
Team Check-in Meeting	D Abeysinghe	10:00 AM
Submit Week 1 Report	D Abeysinghe	5:00 PM

WEEK 2 (Feb 23 - Mar 1) - Design & Technical Setup
Monday, Feb 23
Task	Assigned To	Due
Complete All Wireframes	Mehedi	12:00 PM
Set Up Firebase Project	Manikkuwadura	5:00 PM
Create Database Schema	Krishna	5:00 PM

Tuesday, Feb 24
Task	Assigned To	Due
Start High-Fidelity Mockups	Mehedi	Ongoing
Configure Firebase Auth	Manikkuwadura	End of day
Set Up Firebase Database	Manikkuwadura	End of day

Wednesday, Feb 25
Task	Assigned To	Due
Team Review: Mockups	Mehedi presents	11:00 AM
Finalize Mockups	Mehedi	5:00 PM
Create Mock Student Data	Krishna	5:00 PM

Thursday, Feb 26
Task	Assigned To	Due
Design App Icon	Mehedi	12:00 PM
Design Splash Screen	Mehedi	5:00 PM
Set Up Security Rules	Manikkuwadura	5:00 PM

Friday, Feb 27
Task	Assigned To	Due
Team Check-in	D Abeysinghe	10:00 AM
Week 2 Report	D Abeysinghe	5:00 PM

WEEK 3 (Feb 28 - Mar 6) - Development Sprint 1 (Backend & Login)
Monday, Feb 28
Task	Assigned To	Due
Create Project Structure	Sarfraj	12:00 PM
Upload Mock Data to Firebase	Krishna	5:00 PM
Start Login Screen UI	Mehedi	5:00 PM

Tuesday, Mar 1
Task	Assigned To	Due
Complete Login Screen UI	Mehedi	5:00 PM
Create API Endpoints	Sarfraj	5:00 PM
Implement Data Encryption	Manikkuwadura	5:00 PM

Wednesday, Mar 2
Task	Assigned To	Due
Connect Login to Firebase	Mehedi	5:00 PM
Test Authentication Flow	Manikkuwadura	End of day

Thursday, Mar 3
Task	Assigned To	Due
Implement "Remember Me"	Mehedi	5:00 PM
Bug Fixes - Login	Sarfraj, Mehedi	5:00 PM

Friday, Mar 4
Task	Assigned To	Due
Team Check-in & Demo	D Abeysinghe	10:00 AM
Week 3 Report	D Abeysinghe	5:00 PM

WEEK 4 (Mar 5 - Mar 11) - Development Sprint 2 (ID Card & QR)
Monday, Mar 5
Task	Assigned To	Due
Start ID Card Screen UI	Sarfraj	5:00 PM
Implement Data Fetching	Sarfraj	5:00 PM

Tuesday, Mar 6
Task	Assigned To	Due
Display Student Photo	Sarfraj	5:00 PM
Display Student Details	Sarfraj	5:00 PM
Start QR Code Generator	Sarfraj	5:00 PM

Wednesday, Mar 7
Task	Assigned To	Due
Complete QR Code Generator	Sarfraj	12:00 PM
Add QR Refresh Timer	Sarfraj	5:00 PM
Start Profile Screen	Mehedi	5:00 PM

Thursday, Mar 8
Task	Assigned To	Due
Complete Profile Screen	Mehedi	5:00 PM
Implement Logout	Mehedi	5:00 PM
Add Offline Storage	Sarfraj	5:00 PM

Friday, Mar 9
Task	Assigned To	Due
Team Check-in & Demo	D Abeysinghe	10:00 AM
Week 4 Report	D Abeysinghe	5:00 PM

WEEK 5 (Mar 10 - Mar 16) - Testing & Bug Fixing
Monday, Mar 10
Task	Assigned To	Due
Create Test Plan	Krishna	12:00 PM
Begin Testing - Login	Krishna	5:00 PM

Tuesday, Mar 11
Task	Assigned To	Due
Test ID Card Display	Durgesh	5:00 PM
Test QR Code	Durgesh	5:00 PM
Security Testing	Manikkuwadura	5:00 PM

Wednesday, Mar 12
Task	Assigned To	Due
Test Offline Mode	Krishna	5:00 PM
Fix Bugs Found	Sarfraj, Mehedi	Ongoing
Retest Fixed Bugs	Krishna	End of day

Thursday, Mar 13
Task	Assigned To	Due
User Acceptance Testing (with 3 students)	Durgesh	5:00 PM
Gather Feedback	Durgesh	5:00 PM
Implement Feedback Changes	Sarfraj, Mehedi	5:00 PM

Friday, Mar 14
Task	Assigned To	Due
Final Testing	All	5:00 PM
Week 5 Report	D Abeysinghe	5:00 PM

WEEK 6 (Mar 15 - Mar 21) - Deployment & Launch
Monday, Mar 15
Task	Assigned To	Due
Generate Signed APK	Sarfraj	5:00 PM
Create App Store Listing	Sarfraj	5:00 PM
Prepare User Guide	Mehedi	5:00 PM

Tuesday, Mar 16
Task	Assigned To	Due
Submit to Google Play	Sarfraj	12:00 PM
Prepare Launch Announcement	Durgesh	5:00 PM
Final Security Check	Manikkuwadura	5:00 PM

Wednesday, Mar 17
Task	Assigned To	Due
Team Rehearsal	D Abeysinghe	11:00 AM
Final Review	All	5:00 PM

Thursday, Mar 18 - LAUNCH DAY
Time	Activity	Lead
9:00 AM	Final check	Manikkuwadura
10:00 AM	Send launch announcement	Durgesh
10:00 AM - 5:00 PM	Monitor downloads, fix urgent issues	All on standby
5:00 PM	Launch day report	D Abeysinghe

Friday, Mar 19
Task	Assigned To	Due
Post-Launch Review Meeting	D Abeysinghe	11:00 AM
Collect Week 1 Feedback	Durgesh	5:00 PM
Project Closure Report	D Abeysinghe	5:00 PM

Part 4: Daily Standup Schedule (15 minutes daily)
Time: 9:45 AM - 10:00 AM (Monday-Friday)
Platform: WhatsApp/Teams
Daily Questions:
1. What did you do yesterday?
2. What will you do today?
3. Any blockers?
Day	Standup Lead
Monday	D Abeysinghe
Tuesday	Sarfraj Ahmad
Wednesday	Manikkuwadura De Silva
Thursday	Krishna Bhandari
Friday	Durgesh Bin

Part 5: Milestone Summary
Milestone	Date	Deliverables	Owner
Requirements Complete	Feb 19	Requirements Document	Durgesh
Design Complete	Feb 27	Wireframes, Mockups, Icon	Mehedi
Backend Ready	Mar 4	Firebase setup, Auth working	Manikkuwadura
Login Working	Mar 4	Login screen functional	Mehedi
ID Card Working	Mar 9	ID display, QR code	Sarfraj
Testing Complete	Mar 14	Test reports, bugs fixed	Krishna
App Submitted	Mar 16	APK, Store listing	Sarfraj
LAUNCH	Mar 18	App live	All

Part 6: Trello Automation Rules
Set up these Butler rules in Trello:
Rule	Action
When a card is moved to "Done"	Assign "Completed" label, notify @D Abeysinghe
When a card is in "In Progress" for 3 days	Add "Overdue" label, notify team
Every Monday at 9:00 AM	Move all "To Do (This Week)" to "In Progress" if due this week
When checklist is 100% complete	Move card to "Review/Testing"

Part 7: Responsibility Matrix (Who Does What When)
Task Category	Lead	Support	Review
Requirements	Durgesh	Krishna	All
Data Design	Krishna	Durgesh	Developers
Security	Manikkuwadura	Mehedi	D Abeysinghe
UI Design	Mehedi	Sarfraj	Durgesh
Frontend Dev	Sarfraj	Mehedi	Manikkuwadura
Backend Dev	Manikkuwadura	Sarfraj	Krishna
Testing	Krishna	Durgesh	All
Deployment	Sarfraj	Mehedi	D Abeysinghe
Communication	Durgesh	D Abeysinghe	All

Trello Board Invitation Link
Create your board here: trello.com
Board Template: Use this structure and copy all cards above.
Team Members to Invite:
- d.abeysinghe@student.university
- manikkuwadura@student.university
- sarfraj@student.university
- krishna@student.university
- mehedi@student.university
- durgesh@student.university