DIGITAL STUDENT ID WALLET APP

Project Status Report (Weeks 1-4)

Team: The Thinkers

1. Executive Summary

This report outlines the progress of the Digital Student ID Wallet project from its initiation (Week 1) through the first two development sprints (Week 4). As Project Manager, I confirm that the team has successfully established the foundational infrastructure, design language, and core feature set. The project has completed the Planning, Design, and Technical Setup phases, and is currently midway through Development Sprint 2.

Crucial Note: The project is not yet finished. At this stage, we have achieved a basic, functional prototype. While the core user flow (login, ID card viewing, QR generation) is working, the application is not feature-complete, has not undergone full testing, and is not ready for deployment. Significant work remains in testing, security hardening, and offline functionality.

2. Overall Project Status

| Metric | Status |
| --- | --- |
| Overall Health | 🟡 In Progress / On Track |
| Completion Estimate | ~40% (Core functionality implemented, pending testing, polish, and deployment) |
| Key Milestone | Phase 1 (Foundation) - COMPLETE |
| Key Risk | Scope of testing and bug-fixing phase may be underestimated. |

3. Work Completed (Weeks 1-4)

The team has successfully executed the project plan for the first four weeks. Key achievements include:

Week 1: Planning & Setup (Feb 16 - Feb 22)

- Project Management: Trello board created, kickoff meeting held, and weekly reporting structure established.

- Requirements: The detailed requirements document and data dictionary were drafted and finalized.

- Initial Research: A security requirements analysis was completed, and the GitHub repository was created and shared with all collaborators.

Week 2: Design & Technical Setup (Feb 23 - Mar 1)

- Design: All wireframes (Login, ID Card, Profile) were completed. High-fidelity mockups were created and reviewed by the team. The app icon and splash screen were also designed.

- Backend: The Firebase project was successfully set up, including Firestore database, authentication, and initial security rules. The database schema was defined, and mock student data was generated and uploaded.

Week 3: Development Sprint 1 - Backend & Login (Feb 28 - Mar 4)

- Login Functionality: The login screen UI was built and successfully connected to Firebase Authentication. The "Remember Me" feature was implemented.

- Backend Integration: API endpoints were created, and data encryption for sensitive fields was implemented.

- Outcome: A functioning authentication system is now in place.

Week 4: Development Sprint 2 - ID Card & QR (Mar 5 - Mar 9)

- Core Features: The main ID Card screen was built, successfully fetching and displaying student data, including the profile photo.

- QR Code: The dynamic QR code generator was implemented and is functioning. An auto-refresh timer for the QR code was added as a security measure.

- User Management: The profile screen UI was built, and the logout function was implemented.

4. What Has Been Built (The "Basic" State)

As of the end of Week 4, we have a basic, working prototype. A user can:

- Login securely using their credentials.

- See their Digital Student ID Card displayed on the main screen.

- View their dynamic QR code, which refreshes every 5 minutes for security.

- Navigate to a Profile Screen and successfully log out.

This represents the core user journey but lacks polish, full error handling, and several planned features.

5. Pending Work & Next Steps (Weeks 5-8)

The following critical tasks remain and are being managed in the "Backlog" column of our Trello board:

Immediate Priorities (Weeks 5-6)

- Offline Storage: Implementing local caching so the ID card is viewable without an internet connection.

- Testing: Executing the test plan, including:

  - Functional testing (login, data display).

  - Security testing (attempting to breach Firebase rules).

  - User acceptance testing with real student volunteers.

- Bug Fixing: Addressing issues found during testing.

Future Work (Weeks 7-8+)

- Deployment:

  - Generating a signed APK (Android release build).

  - Preparing Google Play Store listing (description, screenshots).

  - Creating a user guide PDF.

- Project Wrap-up:

  - Final risk register review.

  - Launch day monitoring plan.

  - Final project report.

6. Key Achievements & Risks

| Achievements | Risks & Mitigations |
| --- | --- |
| ✅ All planning and documentation completed on schedule. | ⚠️ Risk: Testing Phase may take longer than planned. Mitigation: Testing cards have been created in Trello and are prioritized for the next sprint. We will begin exploratory testing immediately. |
| ✅ Design system (wireframes/mockups) finalized and approved. | ⚠️ Risk: Offline Storage is a complex feature that is not yet started. Mitigation: A dedicated developer has been assigned to this card, and it is the top priority for the next sprint. |
| ✅ Firebase backend fully configured with authentication and database. |  |
| ✅ Core user flow (Login -> View ID -> QR -> Logout) is functional. |  |

7. Conclusion

The Digital Student ID Wallet project has made strong progress in its first month. The team has successfully laid the groundwork and built a solid foundation, culminating in a basic but functional prototype. As Project Manager, I am satisfied with the team's adherence to the schedule and the quality of work delivered so far.

However, it is crucial to reiterate that the project is not yet complete. The coming weeks will be critical for transforming this prototype into a secure, reliable, and polished application ready for student use. Our focus will now shift from building new features to testing, hardening, and finalizing the product for deployment.

Respectfully submitted,

D. Abeysinghe Mudiyanselage 2454632
Project Manager, The Thinkers
Date: March 22, 2026